## Sheet1
Employee Name: | ISALANYA SAM MWASE
Department: | TECHNICAL | Tesla IT Solutions
Supervisor: | KAMUGASA JULIUS
Start Date | 2024-08-05
End Date | 2024-08-09
Date | Client | Type | Activity | Task Description | Time (Hours) | Support Sheet No.
2024-08-05 | Admin | Project | Development | Worked on deployment of the Human Resource self service portal to IIS sever
2024-08-06 | Admin | Project | Development | Continued work on deployment of the HR self service portal. Worked on the HR self service portal application Component.
2024-08-07 | Admin | Project | Development | Successfully had the applications submission component and stored in the databse for further being worked upon. Debugged email account activation and also MFA account login usung a OTP sent to email.
2024-08-08 | Admin | Admin | Development | Successfully worked upon display of the applications made by the applicants based on the logged in user. This included, the application status, the status of the vacancy. It also entailed the actions which are edit, view and withdrawal of application. I started working on the view of application details for a chosen application by the user.
2024-08-09 | Admin | Admin | Development | I have finished working on the view of applications and the withdrawal of applications actions. Added check on applications to vacancies, once a user has applied to a certain vacancy before, they are notified and redirected to the page where they can edit the application. Also, added more data to be displayed and filled in on the application form for users. Working on completion of the applcation editing and other loopholes.